## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 574/RD/PHE | 23/02/2023 | 23/02/2023 | Resource Division | 31.27 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Laksmania, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03539/2023-2024 | BP-2023-24-566 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 0.65 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Laksmania, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03538/2023-2024 | BP-2023-24-565 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 0.54 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Additional Quotation for TW-II of Laksmania Water supply scheme in the district of Uttar Dinajpur. |  |  | BILL/02075/2024-2025 | BP-2024-25-488 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 0.23 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Implementation of Laksmania and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000031/2023-2024 | 1306/RD/PHE | 12/05/2023 | 01/01/2026 | UNIVERSAL ENTERPRISES | 279.7 | 0 | 0 | 70
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Making compound lighting arrangement with allied works at T/W no. I of Laksmania Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000714/2023-2024 | 2231/MLMD | 18/07/2023 | 05/10/2025 | M/S PARIMAL DAS. | 3.83 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under LAKSMANIA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000464/2023-2024 | 572/RD/PHE | 05/03/2024 | 30/03/2025 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 22.58 | 0 | 0 | 85
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd Tubewell Site and road restoration of Laksmania PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000408/2025-2026 | 1606/RD/PHE | 17/06/2025 | 15/10/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 39.5 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of LAKSMANIA Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | Assistant Engineer - I | Junior Engineer-07 | ORD/000213/2023-2024 | 2197/MLMD | 18/07/2023 | 22/02/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 11.3 | 0 | 0 | 100
10 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. | SM/11897 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of LAKSMANIA Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | Assistant Engineer - I | Junior Engineer-07 | ORD/000214/2023-2024 | 2198/MLMD | 18/07/2023 | 01/03/2025 | HANNAN BUILDERS PVT. LTD. | 11.3 | 0 | 0 | 100
Total | [13 empty] | 400.91 | 0 | 0