## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 2124/RD/PHE | 03/12/2022 | 03/12/2022 | Resource Division | 21.7 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Making compound lighting arrangement with allied works at T/W no. I of Basain Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011690) | Assistant Engineer - I | Junior Engineer-07 | ORD/000713/2023-2024 | 2243/MLMD | 18/07/2023 | 16/10/2023 | M/S CHANDRANATH MUKHERJEE. | 3.83 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Construction of Pump House & Boundary Wall at Basain Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000259/2022-2023 | 385/RD/PHE | 08/02/2023 | 09/04/2023 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 36.15 | 29.65 | 82.03 | 100
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Basain PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000009/2023-2024 | 4003132972 | 16/04/2023 | 01/05/2023 | W.B.S.E.D.C.LTD | 0.56 | 0.56 | 100 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Basain PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000010/2023-2024 | 4003132989 | 16/04/2023 | 01/05/2023 | W.B.S.E.D.C.LTD | 0.45 | 0.45 | 100 | 0
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. |  |  | BILL/00504/2023-2024 | BP-2023-24-129 | 29/09/2023 | 29/09/2023 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | additional quotation of basian TW-I & basian TW-II in the district of Uttar Dinajpur. |  |  | BILL/01598/2024-2025 | BP-2024-25-400 | 29/07/2024 | 29/07/2024 | W.B.S.E.D.C.LTD | 2.47 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Implementation of Basain and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000152/2022-2023 | 1991/RD/PHE | 14/11/2022 | 02/01/2026 | AJIT PRAMANIK AJITPRAMANICK83@GMAIL.COM | 456.96 | 248.8 | 54.45 | 62
9 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BASAIN Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001056/2022-2023 | 0257/MLMD | 24/02/2023 | 16/01/2025 | DEBAPRIYA SAHA | 11.66 | 9.38 | 80.39 | 100
10 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BASAIN Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001057/2022-2023 | 0258/MLMD | 24/02/2023 | 16/01/2025 | DEBAPRIYA SAHA | 11.66 | 0 | 0 | 100
11 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/003385/2023-2024 | 1120/MLMD | 22/03/2024 | 22/05/2024 | DAS CONSTRUCTION | 0.77 | 0.77 | 99.94 | 100
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. | SM/11961 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Basain PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000442/2024-2025 | 3754/RD/PHED | 18/12/2024 | 14/09/2025 | AJIT PRAMANIK | 39.05 | 0 | 0 | 80
Total | [13 empty] | 607.78 | 289.61 | 47.65