## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Raiganj Division | KATAGAON Piped Water Supply Scheme at Chopra Block | SM/12082 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1038/RD/PHE | 04/04/2023 | 04/04/2023 | Resource Division | 24.58 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Chopra | Malda Mechanical | KATAGAON Piped Water Supply Scheme at Chopra Block | SM/12082 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Katagaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014361) | Assistant Engineer - I | Junior Engineer-02 | ORD/000219/2023-2024 | 2209/MLMD | 18/07/2023 | 05/10/2025 | MERCURY ENGINEERING COMPANY. | 27.22 | 0 | 0 | 74
3 | UTTAR DINAJPUR | Chopra | Malda Mechanical | KATAGAON Piped Water Supply Scheme at Chopra Block | SM/12082 | New | Quotation for new service connection at KATAGAON PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12082) |  |  | BILL/01072/2024-2025 | BP-2024-25-311 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 16.37 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Malda Mechanical | KATAGAON Piped Water Supply Scheme at Chopra Block | SM/12082 | New | Quotation for new service connection at KATAGAON PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12082) |  |  | BILL/01075/2024-2025 | BP-2024-25-312 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 5.31 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Chopra | Raiganj Division | KATAGAON Piped Water Supply Scheme at Chopra Block | SM/12082 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
6 | UTTAR DINAJPUR | Chopra | Raiganj Division | KATAGAON Piped Water Supply Scheme at Chopra Block | SM/12082 | New | Providing FHTC in connection with Katagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000003/2025-2026 | 1174/RD/PHE | 23/04/2025 | 08/05/2025 | DIPANKAR SARKAR | 6.94 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Chopra | Raiganj Division | KATAGAON Piped Water Supply Scheme at Chopra Block | SM/12082 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at KATAGAON PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000387/2025-2026 | 2161/RD/PHE | 23/07/2025 | 19/01/2026 | M/S SACHIN KUMAR | 32.55 | 0 | 0 | 0
Total | [13 empty] | 7326.9 | 0 | 0