## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Malda Mechanical | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of MANIKPUR,Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000648/2023-2024 | 4003205417 | 04/08/2023 | 02/11/2023 | W.B.S.E.D.C.LTD | 21.16 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 597/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 25.59 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | New Service Connection charge with Security Deposit for Implementation of Manikpur PH-II WSS under Islampur CCC in the district of Uttar Dinajpur. |  |  | BILL/00496/2023-2024 | BP-2023-24-134 | 29/09/2023 | 29/09/2023 | WEST BENGAL STATE ELETRICITY DISTRIBUTION COMPANY LIMITED | 23.16 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANIKPUR Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000483/2023-2024 | 592/RD/PHE | 05/03/2024 | 01/09/2024 | CHADNI CONSTRUCTION | 22.58 | 0 | 0 | 90
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Implementation of MANIKPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and 2nd Tube Well) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000299/2022-2023 | 548/RD/PHE | 23/02/2023 | 10/10/2025 | UJJWAL DAS NAMEDUTTA@GMAIL.COM | 457.08 | 0 | 0 | 85
6 | UTTAR DINAJPUR | Islampur | Malda Mechanical | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Manikpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014295) | Assistant Engineer - I | Junior Engineer-02 | ORD/000188/2023-2024 | 2114/MLMD | 05/07/2023 | 02/11/2023 | NEOGI ENTERPRISE. | 26.45 | 0 | 0 | 85
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Laying of Additional Pipeline with Land development and pathway for MANIKPUR Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000386/2024-2025 | 3556/RD/PHE | 05/12/2024 | 14/01/2026 | UJJWAL DAS | 65.29 | 0 | 0 | 40
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000357/2024-2025 | 3041/RD/PHE | 03/10/2024 | 13/01/2025 | SISIR KUMAR DUTTA | 1.35 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Providing FHTC in connection with Manikpur Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD ,Junior Engineer, RWS | ORD/000512/2024-2025 | 57/RD/PHE | 03/01/2025 | 29/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 15.76 | 0 | 0 | 65
10 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Islampur | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block | SM/12084 | New | Trial Run For Manikpur PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000715/2024-2025 | 547/RD/PHE | 12/02/2025 | 13/05/2025 | UJJWAL DAS | 0.88 | 0 | 0 | 0
Total | [13 empty] | 664.1 | 0 | 0