## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Malda Mechanical | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of KUNDARGAON, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001552/2023-2024 | 4003151020 | 18/07/2023 | 16/10/2023 | W.B.S.E.D.C.LTD | 3.39 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Islampur | Malda Mechanical | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KUNDARGAON , Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/001941/2023-2024 | 4003194828 | 18/07/2023 | 16/10/2023 | W.B.S.E.D.C.LTD | 4.84 | 0 | 0 | 100
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 617/RD/PHE | 28/02/2023 | 28/02/2023 | Resource Division | 24.12 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Kundargaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014258) | Assistant Engineer - I | Junior Engineer-02 | ORD/000226/2023-2024 | 2214/MLMD | 18/07/2023 | 26/02/2026 | M/S S. S. ENTERPRISE | 27.22 | 0 | 0 | 70
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Additional pipeline and other ancillary works at Kundargaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000365/2024-2025 | 3484/RD/PHE | 02/12/2024 | 16/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 41.22 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Implementation of KUNDARGAON and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rd Tube Well.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000303/2022-2023 | 552/RD/PHE | 23/02/2023 | 12/02/2025 | SANYAL ENTERPRISE | 321.28 | 0 | 0 | 60
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KUNDARGAON Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000549/2024-2025 | 293/RD/PHE | 15/01/2025 | 01/03/2025 | MOON CONSTRUCTION | 22.58 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Trial Run For Kundargaon PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000721/2024-2025 | 553/RD/PHE | 12/02/2025 | 13/05/2025 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Islampur | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for Kundargaon Piped Water Supply Scheme under Islampur Sub-Division PHED under Raiganj Division, PHED., U/D. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000251/2025-2026 | 2042/RD/PHE | 09/07/2025 | 07/10/2025 | M/S RATAN SARKAR & SON | 5.4 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Islampur | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block | SM/12086 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0 | 0 | 100
Total | [13 empty] | 460.71 | 0 | 0