## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Durgapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014156) | Assistant Engineer - I | Junior Engineer-02 | ORD/000223/2023-2024 | 2212/MLMD | 18/07/2023 | 15/11/2023 | SUNRISE ENGINEERING CORPORATION. | 25.3 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of DURGAPUR, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000985/2023-2024 | 4003226066 | 08/09/2023 | 07/12/2023 | W.B.S.E.D.C.LTD | 4.38 | 4.38 | 100 | 100
3 | UTTAR DINAJPUR | Islampur | Malda Mechanical | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of DURGAPUR, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000986/2023-2024 | 4003226068 | 08/09/2023 | 07/12/2023 | W.B.S.E.D.C.LTD | 8.15 | 8.15 | 100 | 100
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Material Requisition To Resource Division |  |  | RTOR000114/2022-2023 | 601/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 20.57 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Protection and Restoration work of damaged flank caused by excavation for water supply project of PHE of Matikunda- Moragoti Road under uttar dinajpur division, PWD. |  |  | BILL/00505/2023-2024 | BP-2023-24-143 | 30/09/2023 | 30/09/2023 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 9.23 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Additional pipeline and other ancillary works at Durgapur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000362/2024-2025 | 3481/RD/PHE | 02/12/2024 | 16/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Durgapur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000363/2024-2025 | 3482/RD/PHE | 02/12/2024 | 01/01/2025 | SHANKAR SAHA | 9.25 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DURGAPUR Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000484/2023-2024 | 593/RD/PHE | 05/03/2024 | 19/04/2024 | M/S LUCKY CONSTRUCTION | 22.58 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Implementation of DURGAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work,2nd & 3rd Tube Well.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000301/2022-2023 | 550/RD/PHE | 23/02/2023 | 10/10/2025 | UJJWAL DAS NAMEDUTTA@GMAIL.COM | 341.08 | 128.44 | 37.66 | 38
10 | UTTAR DINAJPUR | Islampur | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Providing FHTC in connection with Durgapur Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000508/2024-2025 | 53/RD/PHE | 03/01/2025 | 17/02/2025 | APEX ENTERPRISES | 5.59 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Islampur | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block | SM/12087 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Durgapur Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000289/2025-2026 | 1815/RD/PHE | 24/06/2025 | 21/12/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.35 | 0 | 0 | 0
Total | [13 empty] | 487.5 | 140.97 | 28.92