## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 607/RD/PHE | 27/02/2023 | 27/02/2023 | Resource Division | 43.16 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Malda Mechanical | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Pothia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014140) | Assistant Engineer - I | Junior Engineer-02 | ORD/000233/2023-2024 | 2216/MLMD | 18/07/2023 | 15/11/2023 | S. P. CONSTRUCTION | 27.17 | 14.56 | 53.6 | 54
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under POTHIA Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000485/2023-2024 | 594/RD/PHE | 05/03/2024 | 19/04/2024 | PRINCE BUILDERS | 22.58 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Quotation for new service connection at Pothia PH-II (Islampur ccc) district Uttar Dinajpur. |  |  | BILL/03560/2023-2024 | BP-2023-24-590 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 14.25 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Quotation for new service connection at Pothia PH-I (Islampur ccc) |  |  | BILL/03559/2023-2024 | BP-2023-24-589 | 22/02/2024 | 22/02/2024 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Pothia PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000244/2025-2026 | 1464/RD/PHE | 04/06/2025 | 24/06/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 6.18 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Implementation of POTHIA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000332/2022-2023 | 675/RD/PHE | 06/03/2023 | 27/02/2025 | UJJWAL DAS | 511.92 | 277.34 | 54.18 | 20
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Laying of Additional pipeline with other ancillary works at different mouzas of POTHIA PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000370/2024-2025 | 3489/RD/PHE | 02/12/2024 | 02/03/2025 | UJJWAL DAS | 36.3 | 0 | 0 | 50
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000357/2024-2025 | 3041/RD/PHE | 03/10/2024 | 13/01/2025 | SISIR KUMAR DUTTA | 1.35 | 0.19 | 13.89 | 0
10 | UTTAR DINAJPUR | Islampur | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block | SM/12088 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pothia Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000317/2025-2026 | 1986/RD/PHE | 04/07/2025 | 31/12/2025 | AJIT PRAMANIK | 30.94 | 0 | 0 | 0
Total | [13 empty] | 701.85 | 292.09 | 41.62