## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Malda Mechanical | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Besabari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013508) | Assistant Engineer - I | Junior Engineer-02 | ORD/000222/2023-2024 | 2211/MLMD | 18/07/2023 | 15/11/2023 | DEBAPRIYA SAHA | 26.19 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 1039/RD/PHE | 04/04/2023 | 04/04/2023 | Resource Division | 17.39 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Chopra | Malda Mechanical | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Quotation for new service connection at DAKSHIN BESABARI PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12089) |  |  | BILL/01076/2024-2025 | BP-2024-25-309 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 6.55 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Malda Mechanical | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Quotation for new service connection at DAKSHIN BESABARI PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12089) |  |  | BILL/01077/2024-2025 | BP-2024-25-310 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 5.58 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 7213.93 | 136.33 | 1.89 | 30
6 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 10/01/2025 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
7 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Providing FHTC in connection with Dakhshin Besabari Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000004/2025-2026 | 1173/RD/PHE | 23/04/2025 | 08/05/2025 | R. R. CONSTRUCTION | 6.75 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Besabari Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000347/2025-2026 | 1817/RD/PHE | 24/06/2025 | 21/12/2025 | M K ENTERPRISE | 17.34 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Chopra | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block | SM/12089 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at DAKSHIN BESABRI PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000384/2025-2026 | 2096/RD/PHE | 15/07/2025 | 11/01/2026 | M/S SACHIN KUMAR | 33.76 | 0 | 0 | 0
Total | [13 empty] | 7330.08 | 136.33 | 1.86