## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 2187/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 48.12 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Implementation of ALIGANJ and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000256/2022-2023 | 298/RD/PHE | 01/02/2023 | 01/01/2026 | UTTAM SAHA | 707.12 | 139.18 | 19.68 | 65
3 | UTTAR DINAJPUR | Islampur | Malda Mechanical | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Aliganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013513) | Assistant Engineer - I | Junior Engineer-02 | ORD/000225/2023-2024 | 2213/MLMD | 18/07/2023 | 27/03/2026 | M/S D.G.B. ENTERPRISE. | 27.21 | 16.37 | 60.15 | 65
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 579/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 47.6 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Laying of Balance Pipeline with ancillary works for ALIGANJ Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000384/2024-2025 | 3554/RD/PHE | 05/12/2024 | 19/01/2025 | KARTICK BISWAS | 37.13 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under ALIGANJ Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000481/2023-2024 | 590/RD/PHE | 05/03/2024 | 19/04/2024 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 22.52 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 15.01.2025 to 14.07.2025.) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000812/2024-2025 | 301/RD/PHE | 15/01/2025 | 15/07/2025 | MD ZAFAR EQUEBAL | 2.4 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Malda Mechanical | ALIGANJ Piped Water Supply Scheme at Islampur Block | SM/12090 | New | Quotation for new service connection at ALIGANJ PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12090). |  |  | BILL/03198/2024-2025 | BP-2024-25-639 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 5.97 | 0 | 0 | 0
Total | [13 empty] | 898.07 | 155.55 | 17.32