## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 2186/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 30.47 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1217/RD/PHE | 02/05/2023 | 02/05/2023 | Resource Division | 30.24 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of patagora- Moragoti Road under Uttar Dinajpur Division, PWD. |  |  | BILL/00507/2023-2024 | BP-2023-24-145 | 30/09/2023 | 30/09/2023 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 6.39 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Construction of concrete pathway ,Land development and other ancillary works for AGDIMTI Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division, PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000420/2024-2025 | 3583/RD/PHE | 05/12/2024 | 04/01/2025 | SOVAN KUMAR ROY | 10.96 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Quotation for new service connection at AGDIMTI PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00218/2024-2025 | BP-2024-25-93 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 9.15 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | MDR T01, RAMKRISHHNAPUR TO MDR T10 DIMTI VIA BHARDRAKALI (ROAD CODE T06) |  |  | BILL/00107/2024-2025 | BP-2024-25-73 | 12/06/2024 | 12/06/2024 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 12.52 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Malda Mechanical | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Quotation for new service connection at AGDIMTI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00224/2024-2025 | BP-2024-25-94 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 6.33 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Implementation of AGDIMTI and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under RaiganjDivision. PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000001/2023-2024 | 1035/RD/PHE | 04/04/2023 | 05/03/2026 | SOVAN KUMAR ROY | 563.17 | 0 | 0 | 71
9 | UTTAR DINAJPUR | Islampur | Malda Mechanical | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Agdimti Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013515) | Assistant Engineer - I | Junior Engineer-02 | ORD/000231/2023-2024 | 2215/MLMD | 18/07/2023 | 31/10/2025 | DIPALI CONSTRUCTION. | 27.17 | 0 | 0 | 67
10 | UTTAR DINAJPUR | Islampur | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
11 | UTTAR DINAJPUR | Islampur | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block | SM/12091 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under AGDIMTI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000480/2023-2024 | 589/RD/PHE | 05/03/2024 | 03/06/2024 | BABA LOKNATH ENTERPRISE | 22.57 | 0 | 0 | 0
Total | [13 empty] | 723.75 | 0 | 0