## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 2182/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 33.1 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | Implementation of GAISAL and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000242/2022-2023 | 293/RD/PHE | 01/02/2023 | 31/08/2026 | UTTAM SAHA | 554.3 | 273.92 | 49.42 | 70
3 | UTTAR DINAJPUR | Islampur | Malda Mechanical | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Gaisal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013516) | Assistant Engineer - I | Junior Engineer-02 | ORD/000235/2023-2024 | 2218/MLMD | 18/07/2023 | 29/10/2025 | MANIK CHANDRA SAHA. | 27.22 | 19.59 | 71.99 | 73
4 | UTTAR DINAJPUR | Islampur | Malda Mechanical | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Gaisal, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000791/2023-2024 | 4003204407 | 23/08/2023 | 21/11/2023 | W.B.S.E.D.C.LTD | 8.02 | 8.02 | 100 | 100
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Gaisal, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000422/2023-2024 | 4003199236 | 25/07/2023 | 23/10/2023 | W.B.S.E.D.C.LTD | 12.15 | 12.15 | 100 | 100
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 580/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 33.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | Construction Of Single Row 1200 Mm Dia Np3 Hume Pipe Culvert In Front Of Gaisal Head Works Site For Approach Road Under Raiganj Division, Phe Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000413/2024-2025 | 3577/RD/PHE | 05/12/2024 | 03/06/2025 | MIZANUR RAHAMAN | 3.13 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | Laying of Additional Pipeline with land development and path way for GAISAL Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000249/2025-2026 | 1485/RD/PHE | 04/06/2025 | 19/07/2025 | M/S LUCKY CONSTRUCTION | 54.57 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Islampur | Raiganj Division | GAISAL Piped Water Supply Scheme at Islampur Block | SM/12092 | New | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C. vehicle no. WB58CB7128) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. period from 08/01/2026 to 07/07/2026. |  |  | ORD/000747/2025-2026 | 19/RD/PHE | 07/01/2026 | 07/07/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 2.4 | 0 | 0 | 0
Total | [13 empty] | 727.99 | 313.68 | 43.09