## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 | New | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 2185/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 32.36 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Islampur | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 | New | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 583/RD/PHE | 24/02/2023 | 24/02/2023 | Resource Division | 32.13 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 | New | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of patagora- Moragoti Road under Uttar Dinajpur Division, PWD. |  |  | BILL/00507/2023-2024 | BP-2023-24-145 | 30/09/2023 | 30/09/2023 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 6.39 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 | New | Implementation of BARAKHANTI and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000253/2022-2023 | 297/RD/PHE | 01/02/2023 | 28/03/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 617.49 | 0 | 0 | 30
5 | UTTAR DINAJPUR | Islampur | Malda Mechanical | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Barakhanti Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013549) | Assistant Engineer - I | Junior Engineer-02 | ORD/000220/2023-2024 | 2210/MLMD | 18/07/2023 | 04/11/2025 | SUBRATA SAHA | 27.22 | 0 | 0 | 73
6 | UTTAR DINAJPUR | Islampur | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARAKHANTI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000482/2023-2024 | 591/RD/PHE | 05/03/2024 | 19/04/2024 | M/S DUTTA ENTERPRISE | 22.57 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 | New | Additional pipeline and other ancillary works at Barakhanti piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000360/2024-2025 | 3479/RD/PHE | 02/12/2024 | 16/01/2025 | M/S BHOWMIK ENTERPRISE | 31.05 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block | SM/12093 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
Total | [13 empty] | 774.02 | 0 | 0