## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 2180/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 39.53 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of CHAK DILAL PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000432/2023-2024 | 4003202414 | 02/08/2023 | 31/10/2023 | W.B.S.E.D.C.LTD | 3.15 | 0 | 0 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Chak Dilal PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001878/2023-2024 | 4003202777 | 04/08/2023 | 02/11/2023 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 100
4 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Implementation of CHAKDILAL and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000241/2022-2023 | 292/RD/PHE | 01/02/2023 | 01/01/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 620.92 | 0 | 0 | 58
5 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chak Dilal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012812) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000172/2023-2024 | 2093/MLMD | 04/07/2023 | 08/02/2026 | DAS CONSTRUCTION | 25.47 | 0 | 0 | 85
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Wayleave/ track crossing proposal with application ID: NFR-KIR-2024-WL-20 under Katihar Division of North East Frontier Railway in connection with Chakdilal PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. |  |  | BILL/00178/2024-2025 | BP-2024-25-106 | 09/07/2024 | 09/07/2024 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 0.12 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Wayleave/ track crossing proposal with application ID: NFR-KIR-2024-WL-20 under Katihar Division of Northeast Frontier Railway in connection with Chakdilal PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. |  |  | BILL/00271/2024-2025 | BP-2024-25-177 | 29/08/2024 | 29/08/2024 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.81 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chakdilal PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000425/2024-2025 | 3737/RD/PHE | 18/12/2024 | 02/05/2025 | AJIT PRAMANIK | 68.07 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Trial Run For Chakdilal PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000673/2024-2025 | 519/RD/PHE | 12/02/2025 | 13/05/2025 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
Total | [13 empty] | 770.84 | 0 | 0