## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 2180/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 39.53 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of CHAK DILAL PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000432/2023-2024 | 4003202414 | 02/08/2023 | 31/10/2023 | W.B.S.E.D.C.LTD | 3.15 | 3.15 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Chak Dilal PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001878/2023-2024 | 4003202777 | 04/08/2023 | 02/11/2023 | W.B.S.E.D.C.LTD | 5.89 | 5.89 | 100 | 100
4 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Implementation of CHAKDILAL and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000241/2022-2023 | 292/RD/PHE | 01/02/2023 | 01/07/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 620.92 | 285.78 | 46.03 | 58
5 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chak Dilal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012812) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000172/2023-2024 | 2093/MLMD | 04/07/2023 | 08/06/2026 | DAS CONSTRUCTION | 25.47 | 21.83 | 85.73 | 85
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Wayleave/ track crossing proposal with application ID: NFR-KIR-2024-WL-20 under Katihar Division of North East Frontier Railway in connection with Chakdilal PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. |  |  | BILL/00178/2024-2025 | BP-2024-25-106 | 09/07/2024 | 09/07/2024 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 0.12 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Wayleave/ track crossing proposal with application ID: NFR-KIR-2024-WL-20 under Katihar Division of Northeast Frontier Railway in connection with Chakdilal PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. |  |  | BILL/00271/2024-2025 | BP-2024-25-177 | 29/08/2024 | 29/08/2024 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.81 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chakdilal PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000425/2024-2025 | 3737/RD/PHE | 18/12/2024 | 02/05/2025 | AJIT PRAMANIK | 68.07 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Trial Run For Chakdilal PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000673/2024-2025 | 519/RD/PHE | 12/02/2025 | 13/05/2025 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAKDILAL Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000528/2023-2024 | 595/RD/PHE | 05/03/2024 | 31/07/2024 | M/S. ROY & CO. | 11.27 | 0 | 0 | 100
11 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAKDILAL Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000527/2023-2024 | 580/RD/PHE | 05/03/2024 | 31/07/2024 | M C CONSTRUCTION | 11.27 | 0 | 0 | 100
12 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Jack Pushing of M.S. Pipe of 200 mm dia. Through 600 mm dia. M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 52/4 to 52/5 near Radhikapur Railway Station (RDP) for Chakdilal and it's adjoining mouzas water supply scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur.(Phase-II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000138/2024-2025 | 2831/RD/PHE | 23/09/2024 | 22/01/2025 | M/S TRILOCHAN CONSTRUCTION CO | 33.21 | 0 | 0 | 100
13 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 16.04.2024 to 19.04.2024. |  |  | BILL/00590/2024-2025 | BP-2024-25-301 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.04 | 0 | 0 | 0
14 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 23.04.2024 to 26.04.2024 and 29.04.2024. |  |  | BILL/00591/2024-2025 | BP-2024-25-302 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.06 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 02.05.2024 to 03.05.2024 and 06.05.2024 to 07.05.2024 and 09.05.2024. |  |  | BILL/00592/2024-2025 | BP-2024-25-303 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.05 | 0 | 0 | 0
16 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block | SM/12094 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 13.05.2024 to 16.05.2024. |  |  | BILL/00593/2024-2025 | BP-2024-25-304 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.04 | 0 | 0 | 0
Total | [13 empty] | 826.79 | 316.65 | 38.3