## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 2179/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 32.43 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Implementation of CHAPOIR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000228/2022-2023 | 291/RD/PHE | 01/02/2023 | 21/06/2026 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 570.71 | 343.83 | 60.25 | 56
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chapair Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012816) | Assistant Engineer - I | Junior Engineer-07 | ORD/000173/2023-2024 | 2094/MLMD | 04/07/2023 | 18/10/2025 | DILIP MAHATO. | 26.31 | 19.22 | 73.07 | 86
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of CHAPAIR PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000634/2023-2024 | 4003202775 | 08/08/2023 | 06/11/2023 | W.B.S.E.D.C.LTD | 5.2 | 5.2 | 100 | 100
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Additional pipe line laying for Chapoir Piped Water Supply Scheme at Kaliyaganj Block of Uttar Diunajpur District Under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000141/2024-2025 | 2837/RD/PHE | 23/09/2024 | 23/10/2024 | M/S P.S. ENTERPRISE | 20.64 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chapor PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000460/2024-2025 | 3778/RD/PHE | 19/12/2024 | 02/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 57.12 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAPAIR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000474/2023-2024 | 582/RD/PHE | 05/03/2024 | 01/09/2024 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.87 | 5.53 | 24.17 | 50
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w L042 BHABAK to CHAPOIR (Package No. WB15302: Under DLP), under coverage of Chapoir PWSS (SM/12095) |  |  | BILL/00477/2024-2025 | BP-2024-25-278 | 08/10/2024 | 08/10/2024 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.68 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of CHAPAIR PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02458/2023-2024 | BP-2023-24-400 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 10.81 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Trial Run For Chapoir PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000701/2024-2025 | 542/RD/PHE | 12/02/2025 | 13/05/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block | SM/12095 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chapoir Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000260/2025-2026 | 1621/RD/PHE | 19/06/2025 | 16/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.58 | 0 | 0 | 0
Total | [13 empty] | 778.22 | 373.78 | 48.03