## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of UTTAR MIRZAPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000431/2023-2024 | 4003202233 | 02/08/2023 | 31/10/2023 | W.B.S.E.D.C.LTD | 3.17 | 3.17 | 100 | 100
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of UTTAR MIRZAPUR, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001514/2023-2024 | 4003224928 | 08/09/2023 | 07/12/2023 | W.B.S.E.D.C.LTD | 3.64 | 3.64 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 28/RD/PHE | 06/01/2023 | 06/01/2023 | Resource Division | 29.02 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,of Uttar Mirzapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012989) | Assistant Engineer - I | Junior Engineer-07 | ORD/000161/2023-2024 | 2086/MLMD | 04/07/2023 | 01/11/2023 | NEOGI ENTERPRISE. | 24.39 | 21.8 | 89.4 | 89
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | Implementation of UTTAR MIRZAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000197/2022-2023 | 66/RD/PHE | 16/01/2023 | 01/01/2026 | SANYAL ENTERPRISE | 277.69 | 174.66 | 62.9 | 65
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under UTTAR MIRZADPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000529/2023-2024 | 588/RD/PHE | 05/03/2024 | 19/04/2024 | LAXMI ENTERPRISE (DIPAK MISHRA) | 11.29 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Uttar Mirzapur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000475/2024-2025 | 08/RD/PHE | 02/01/2025 | 16/02/2025 | UTTAM SAHA | 51.89 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | Trial Run For Uttar Mirzapur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000677/2024-2025 | 523/RD/PHE | 12/02/2025 | 13/05/2025 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block | SM/12096 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under UTTAR MIRZADPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000530/2023-2024 | 596/RD/PHE | 05/03/2024 | 14/04/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 11.29 | 0 | 0 | 80
Total | [13 empty] | 413.25 | 203.27 | 49.19