## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 2190/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 44.2 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | New | Implementation of PURGRAM and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000201/2022-2023 | 70/RD/PHE | 16/01/2023 | 16/01/2024 | SANYAL ENTERPRISE | 365.19 | 233.24 | 63.87 | 70
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of PURGRAM, PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001302/2022-2023 | 4003123574 | 31/03/2023 | 30/03/2024 | W.B.S.E.D.C.LTD | 0.74 | 0.74 | 100 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Purgram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013010) | Assistant Engineer - I | Junior Engineer-07 | ORD/000162/2023-2024 | 2087/MLMD | 04/07/2023 | 14/10/2025 | KARMAKAR CONSTRICTION. | 26.42 | 23.94 | 90.61 | 90
5 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.II of Purgram PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001880/2023-2024 | 4003225016 | 08/09/2023 | 07/12/2023 | W.B.S.E.D.C.LTD | 4 | 4 | 100 | 100
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Purgram PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000476/2024-2025 | 09/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 38.95 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | New | Trial Run For Purgram PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000680/2024-2025 | 526/RD/PHE | 12/02/2025 | 13/05/2025 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12097 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purgram Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 40 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000261/2025-2026 | 1626/RD/PHE | 19/06/2025 | 16/12/2025 | AJIT PRAMANIK | 18.73 | 0 | 0 | 0
Total | [13 empty] | 499.11 | 261.92 | 52.48