## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Laxmipur PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000630/2023-2024 | 4003202783 | 07/08/2023 | 05/11/2023 | W.B.S.E.D.C.LTD | 5.11 | 5.11 | 100 | 100
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Uttar Laxmipur PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000632/2023-2024 | 4003202768 | 08/08/2023 | 06/11/2023 | W.B.S.E.D.C.LTD | 4.72 | 4.72 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 30/RD/PHE | 06/01/2023 | 06/01/2023 | Resource Division | 24.11 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Laxmipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013025) | Assistant Engineer - I | Junior Engineer-07 | ORD/000109/2023-2024 | 1117/MLMD | 23/06/2023 | 21/10/2023 | S.P. ENTERPRISE (KOLKATA) | 25.13 | 21.32 | 84.83 | 84
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Implementation of UTTAR LAKSHMIPUR andit's adjoining mouzas Pipe Water Supply Scheme at KALIYAGANJ BLOCK of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000200/2022-2023 | 69/RD/PHE | 16/01/2023 | 11/11/2024 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 232.09 | 134.64 | 58.01 | 70
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.37 | 7.34 | 100
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Balance UPVC Pipe Line of Uttar Laxmipur PWSS at Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000065/2024-2025 | 2228/RD/PHE | 23/07/2024 | 22/08/2024 | M/S MAA TARA CONSTRUCTION | 11.06 | 2.92 | 26.37 | 100
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 26.12.2023 to 29.12.2023. |  |  | BILL/00610/2024-2025 | BP-2024-25-311 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.05 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 02.01.2024 to 05.01.2024. |  |  | BILL/00611/2024-2025 | BP-2024-25-312 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.05 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Hiring charges of vehicle with fuel, hired for site works of Raiganj Sub Division under Raiganj Division PHE Dte. for the period from 08.01.2024 to 11.01.2024 and 15.01.2024. |  |  | BILL/00612/2024-2025 | BP-2024-25-313 | 24/01/2025 | 24/01/2025 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 0.06 | 0 | 0 | 0
Total | [13 empty] | 307.37 | 169.07 | 55.01