## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Laxmipur PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000630/2023-2024 | 4003202783 | 07/08/2023 | 05/11/2023 | W.B.S.E.D.C.LTD | 5.11 | 0 | 0 | 100
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Uttar Laxmipur PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000632/2023-2024 | 4003202768 | 08/08/2023 | 06/11/2023 | W.B.S.E.D.C.LTD | 4.72 | 0 | 0 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 30/RD/PHE | 06/01/2023 | 06/01/2023 | Resource Division | 24.11 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Laxmipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013025) | Assistant Engineer - I | Junior Engineer-07 | ORD/000109/2023-2024 | 1117/MLMD | 23/06/2023 | 21/10/2023 | S.P. ENTERPRISE (KOLKATA) | 25.13 | 0 | 0 | 84
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12098 | New | Implementation of UTTAR LAKSHMIPUR andit's adjoining mouzas Pipe Water Supply Scheme at KALIYAGANJ BLOCK of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000200/2022-2023 | 69/RD/PHE | 16/01/2023 | 11/11/2024 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 232.09 | 0 | 0 | 70
Total | [13 empty] | 291.16 | 0 | 0