## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 2181/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 27.75 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PALIHAR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000433/2023-2024 | 4003202403 | 02/08/2023 | 31/10/2023 | W.B.S.E.D.C.LTD | 3.7 | 3.7 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of PALIHAR PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001952/2023-2024 | 4003224937 | 08/09/2023 | 07/12/2023 | W.B.S.E.D.C.LTD | 3.2 | 3.2 | 100 | 100
4 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | Implementation of PALIHAR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000249/2022-2023 | 295/RD/PHE | 01/02/2023 | 01/01/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 509.77 | 321.96 | 63.16 | 67
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PALIHAR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000477/2023-2024 | 585/RD/PHE | 05/03/2024 | 19/04/2024 | M/S ARITRA DUTTA | 22.57 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | Additional quotation for palihar water supply scheme TW-II in the district of uttar dinajpur |  |  | BILL/01167/2024-2025 | BP-2024-25-352 | 24/06/2024 | 24/06/2024 | W.B.S.E.D.C.LTD | 1.07 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Palihar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013030) | Assistant Engineer - I | Junior Engineer-07 | ORD/000111/2023-2024 | 1119/MLMD | 23/06/2023 | 07/12/2025 | DEY ENTERPRISE.. | 26.36 | 20.01 | 75.89 | 84
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Palihar PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000474/2024-2025 | 07/RD/PHE | 02/01/2025 | 16/02/2025 | AJIT PRAMANIK | 58.77 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12099 | New | Trial Run For Palihar PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000676/2024-2025 | 522/RD/PHE | 12/02/2025 | 13/05/2025 | AJIT PRAMANIK | 0.88 | 0 | 0 | 0
Total | [13 empty] | 654.06 | 348.87 | 53.34