## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SINTAIR, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000297/2023-2024 | 4003195013 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 2.56 | 2.56 | 100 | 100
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SINTAIR, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000298/2023-2024 | 4003194802 | 18/07/2023 | 16/10/2023 | W.B.S.E.D.C.LTD | 2.81 | 2.81 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 | New | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 27/RD/PHE | 06/01/2023 | 06/01/2023 | Resource Division | 31.09 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 | New | Implementation of SINTAIR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000212/2022-2023 | 72/RD/PHE | 16/01/2023 | 01/01/2026 | SANYAL ENTERPRISE ABHIJITSANYAL2010@GMAIL.COM | 405.17 | 251.5 | 62.07 | 55
5 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sintair Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012780) | Assistant Engineer - I | Junior Engineer-07 | ORD/000112/2023-2024 | 1120/MLMD | 23/06/2023 | 21/10/2023 | DEY ENTERPRISE [HOWRAH] | 25.23 | 21.37 | 84.71 | 84
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SINTAIR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000479/2023-2024 | 587/RD/PHE | 05/03/2024 | 19/04/2024 | M/S KALYAN | 22.57 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sintair PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000477/2024-2025 | 10/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 58.34 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12100 | New | Trial Run For Sintair PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000678/2024-2025 | 524/RD/PHE | 12/02/2025 | 13/05/2025 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
Total | [13 empty] | 548.64 | 278.24 | 50.71