## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 | New | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 2189/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 33.71 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of MADHABPUR, PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000099/2023-2024 | 4003123589 | 04/04/2023 | 03/04/2024 | W.B.S.E.D.C.LTD | 0.63 | 0.63 | 100 | 0
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of MADHABPUR, PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000098/2023-2024 | 4003123584 | 04/04/2023 | 03/04/2024 | W.B.S.E.D.C.LTD | 0.74 | 0.74 | 100 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 | New | Implementation of MADHABPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000202/2022-2023 | 71/RD/PHE | 16/01/2023 | 01/08/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 366.24 | 206.74 | 56.45 | 60
5 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Madhabpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013032) | Assistant Engineer - I | Junior Engineer-07 | ORD/000115/2023-2024 | 1134/MLMD | 26/06/2023 | 23/12/2023 | MAA BHABOTARINE ENTERPRISE. | 25.36 | 22.87 | 90.18 | 90
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 | New | :Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Shibpur Madanpur Pacca Rasta - Kunarhat Tala Pacca Rasta ( WB15296 : Under DLP) caused due to pipe laying by PHED under Madhabpur PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. |  |  | BILL/00478/2024-2025 | BP-2024-25-279 | 08/10/2024 | 08/10/2024 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 3.2 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Madhabpur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000427/2024-2025 | 3739/RD/PHE | 18/12/2024 | 02/05/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 23.53 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12101 | New | Trial Run For Madhabpur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000675/2024-2025 | 521/RD/PHE | 12/02/2025 | 13/05/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
Total | [13 empty] | 454.29 | 230.99 | 50.85