## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 2188/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 21.78 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHANDIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001515/2023-2024 | 4003224917 | 08/09/2023 | 07/12/2023 | W.B.S.E.D.C.LTD | 3.21 | 3.21 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of CHANDIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001516/2023-2024 | 4003224948 | 08/09/2023 | 07/12/2023 | W.B.S.E.D.C.LTD | 3.87 | 3.87 | 100 | 100
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chandipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012771) | Assistant Engineer - I | Junior Engineer-07 | ORD/000336/2023-2024 | 2335/MLMD | 26/07/2023 | 23/11/2023 | ORIENTAL ENGINEERING CO. | 25.19 | 20.56 | 81.62 | 85
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHANDIPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000473/2023-2024 | 581/RD/PHE | 05/03/2024 | 19/04/2024 | TRINAYANI ENTERPRISE | 22.58 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Chandipur PWSS ,Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03392/2023-2024 | BP-2023-24-503 | 01/02/2024 | 01/02/2024 | W.B.S.E.D.C.LTD | 4.22 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 | New | Implementation of CHANDIPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000207/2022-2023 | 76/RD/PHE | 16/01/2023 | 01/07/2026 | PRASENJIT BASAK PROSENJITBASAK44@GMAIL.COM | 253.54 | 144.37 | 56.94 | 25
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12102 | New | Balance Distribution system of Laying Pipeline with FHTC under Chandipur Piped Water Supply Scheme at Kaliyaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dijanpur. (Phase-II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000122/2024-2025 | 3012/RD/PHE | 03/10/2024 | 10/02/2026 | PRASENJIT BASAK PROSENJITBASAK44@GMAIL.COM | 66.23 | 0 | 0 | 50
Total | [13 empty] | 400.61 | 172 | 42.93