## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 | New | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 2191/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 28.04 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KHATSA, PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000100/2023-2024 | 4003123596 | 04/04/2023 | 03/04/2024 | W.B.S.E.D.C.LTD | 0.45 | 0.45 | 100 | 0
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Khatsa PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000008/2023-2024 | 4003123608 | 04/04/2023 | 19/04/2023 | W.B.S.E.D.C.LTD | 0.56 | 0.56 | 100 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 | New | Implementation of KHATSA and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000214/2022-2023 | 73/RD/PHE | 16/01/2023 | 10/01/2025 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 464.26 | 262.76 | 56.6 | 53
5 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Khatsa Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012769) | Assistant Engineer - I | Junior Engineer-07 | ORD/000114/2023-2024 | 1133/MLMD | 26/06/2023 | 14/09/2025 | MANIK CHANDRA SAHA. | 25.28 | 22.83 | 90.3 | 90
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KHATSA Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000475/2023-2024 | 583/RD/PHE | 05/03/2024 | 19/04/2024 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 22.58 | 0 | 0 | 100
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Khatsa PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000426/2024-2025 | 3738/RD/PHE | 18/12/2024 | 18/03/2025 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 9.83 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12103 | New | Trial Run For Khatsa PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000672/2024-2025 | 518/RD/PHE | 12/02/2025 | 13/05/2025 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
Total | [13 empty] | 551.87 | 286.6 | 51.93