## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BEURJHARI PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000435/2023-2024 | 4003202432 | 02/08/2023 | 31/10/2023 | W.B.S.E.D.C.LTD | 4.77 | 4.77 | 100 | 100
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of BEURJHARI PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000628/2023-2024 | 4003202773 | 07/08/2023 | 05/11/2023 | W.B.S.E.D.C.LTD | 5.6 | 5.6 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 31/RD/PHE | 06/01/2023 | 06/01/2023 | Resource Division | 22.57 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Beurjhari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012758) | Assistant Engineer - I | Junior Engineer-07 | ORD/000108/2023-2024 | 1116/MLMD | 23/06/2023 | 21/10/2023 | ASHUTOSH DAS AND CO. | 25.17 | 20.43 | 81.18 | 87
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | Assistant Engineer RSD |  | ORD/000409/2024-2025 | 3045/RD/PHE | 04/10/2024 | 02/01/2025 | ARNAB DUTTA | 1.2 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer HQ | Estimator | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 28/06/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 1.18 | 24.69 | 100
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entireRaiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000408/2024-2025 | 1981/RD/PHE | 29/06/2024 | 13/01/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.6 | 0.4 | 15.35 | 100
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Beurjhari PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000424/2024-2025 | 3736/RD/PHE | 18/12/2024 | 02/05/2025 | BHOLA PAUL | 20.01 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | Trial Run For Beurjhari PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000700/2024-2025 | 541/RD/PHE | 12/02/2025 | 13/05/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.87 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12104 | New | Implementation of BEURJHARI and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000198/2022-2023 | 67/RD/HE | 16/01/2023 | 31/12/2024 | BHOLA PAUL | 223.52 | 140.14 | 62.7 | 80
Total | [13 empty] | 311.12 | 172.53 | 55.45