## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 2183/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 48.49 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. |  |  | BILL/00504/2023-2024 | BP-2023-24-129 | 29/09/2023 | 29/09/2023 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Rampur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012698) | Assistant Engineer - I | Junior Engineer-07 | ORD/000362/2023-2024 | 2371/MLMD | 28/07/2023 | 27/10/2025 | WEST BENGAL ENGINEERING COMPANY. | 24.97 | 0 | 0 | 42
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Rampur Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03534/2023-2024 | BP-2023-24-554 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 2.87 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Rampur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03535/2023-2024 | BP-2023-24-555 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 6.87 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | Additional Quotation of Rampur Water Supply Scheme Pump House-I in the Dist of Uttar Dinajpur. |  |  | BILL/01068/2024-2025 | BP-2024-25-308 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 6.79 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | Implementation of RAMPUR and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000245/2022-2023 | 294/RD/PHE | 01/02/2023 | 01/01/2026 | UTTAM SAHA | 588.22 | 175.25 | 29.79 | 40
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Rampur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000444/2024-2025 | 3756/RD/PHED | 18/12/2024 | 31/03/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 95.53 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAMPUR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000478/2023-2024 | 586/RD/PHE | 05/03/2024 | 28/02/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 22.82 | 0 | 0 | 90
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12105 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Rampur Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000275/2025-2026 | 1796/RD/PHE | 24/06/2025 | 21/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.92 | 0 | 0 | 0
Total | [13 empty] | 850.01 | 175.25 | 20.62