## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 2192/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 35.44 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhitihar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012695) | Assistant Engineer - I | Junior Engineer-07 | ORD/000113/2023-2024 | 1121/MLMD | 23/06/2023 | 21/10/2023 | ORIENTAL ENGINEERING CO. | 25.95 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BHITIHAR PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000426/2023-2024 | 4003196243 | 29/07/2023 | 27/10/2023 | W.B.S.E.D.C.LTD | 4.24 | 4.24 | 100 | 100
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bhitihar, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03542/2023-2024 | BP-2023-24-569 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 6.39 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | Additional Quotation of TW-II of Bhitihar water supply scheme in the district of Uttar Dinajpur. |  |  | BILL/01599/2024-2025 | BP-2024-25-399 | 29/07/2024 | 29/07/2024 | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of BHITIHAR,PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03393/2023-2024 | BP-2023-24-502 | 01/02/2024 | 01/02/2024 | W.B.S.E.D.C.LTD | 3.15 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | Implementation of BHITIHAR andit's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000206/2022-2023 | 75/RD/PHE | 16/01/2023 | 02/01/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 503.79 | 90.7 | 18 | 30
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHITIHAR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000470/2023-2024 | 578/RD/PHE | 05/03/2024 | 14/04/2025 | RAKSHIT TRADERS | 22.58 | 0 | 0 | 100
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12106 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhitihar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000482/2024-2025 | 15/RD/PHE | 02/01/2025 | 16/02/2025 | AJIT PRAMANIK | 87.65 | 0 | 0 | 0
Total | [13 empty] | 692.73 | 94.94 | 13.7