## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Balas PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001167/2022-2023 | 4003123615 | 31/03/2023 | 15/04/2023 | W.B.S.E.D.C.LTD | 0.63 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Balas PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/001166/2022-2023 | 4003123622 | 31/03/2023 | 15/04/2023 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 | New | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 32/RD/PHE | 06/01/2023 | 06/01/2023 | Resource Division | 22.64 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement and allied works at T/W no. I of Balas Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012635) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000117/2023-2024 | 1136/MLMD | 26/06/2023 | 12/01/2026 | HANNAN BUILDERS PVT. LTD. | 26.32 | 0 | 0 | 90
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 | New | Implementation of BALAS and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000199/2022-2023 | 68/RD/PHE | 16/01/2023 | 01/01/2026 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 359.92 | 0 | 0 | 70
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Balas PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000495/2024-2025 | 28/RD/PHE | 02/01/2025 | 16/02/2025 | BHOLA PAUL | 44.41 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 | New | Trial Run For Balas PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000681/2024-2025 | 527/RD/PHE | 12/02/2025 | 13/05/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district | SM/12107 | New | Balance distribution System of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BALAS Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000468/2023-2024 | 576/RD/PHE | 05/03/2024 | 19/04/2024 | BHOLA PAUL | 22.89 | 0 | 0 | 80
Total | [13 empty] | 478.44 | 0 | 0