## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 2200/RD/PHE | 14/12/2022 | 14/12/2022 | Resource Division | 28.55 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Implementation of ADAIR and its adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte(2nd Call). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000325/2022-2023 | 621/RD/PHE | 28/02/2023 | 28/05/2024 | M/S SOMNATH KUNDU | 338.34 | 0 | 0 | 60
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | Assistant Engineer RSD |  | ORD/000409/2024-2025 | 3045/RD/PHE | 04/10/2024 | 02/01/2025 | ARNAB DUTTA | 1.2 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Adiar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000443/2024-2025 | 3755/RD/PHED | 18/12/2024 | 01/02/2025 | M/S SOMNATH KUNDU | 30.08 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Laying distribution of rising main and Balance Pipeline for Implementation of ADIAR and its adjoining mouzas Piped Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. (Phase-1) | Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000063/2024-2025 | 2226/RD/PHE | 23/07/2024 | 21/09/2024 | M/S SOMNATH KUNDU | 32.67 | 0 | 0 | 63
6 | UTTAR DINAJPUR | Raiganj | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01224/2023-2024 | BP-2024-25-24 | 24/04/2024 | 24/04/2024 | EXECUTIVE ENGINEER PWD ROADS | 5.18 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Additional Quotation for TW-II of Adiar Water Supply Scheme in the District of Uttar Dinajpur. |  |  | BILL/02074/2024-2025 | BP-2024-25-487 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Adiar, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03499/2023-2024 | BP-2023-24-519 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 2.53 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Adiar, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03500/2023-2024 | BP-2023-24-520 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 6.12 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Adiar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012052) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000398/2023-2024 | 2456/MLMD | 04/08/2023 | 23/03/2026 | M/S D.G.B. ENTERPRISE. | 26.47 | 0 | 0 | 90
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Trial Run For Adiar PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000698/2024-2025 | 539/RD/PHE | 12/02/2025 | 13/05/2025 | M/S SOMNATH KUNDU | 0.88 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Raiganj | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12108 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Adiar Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000290/2025-2026 | 1816/RD/PHE | 24/06/2025 | 21/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 19.35 | 0 | 0 | 0
Total | [13 empty] | 492.1 | 0 | 0