## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 2199/RD/PHE | 14/12/2022 | 14/12/2022 | Resource Division | 59.08 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Runia PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000448/2024-2025 | 3760/RD/PHED | 18/12/2024 | 01/02/2025 | AJIT PRAMANIK | 74.5 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Runia, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03531/2023-2024 | BP-2023-24-551 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 5.83 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Runia Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03530/2023-2024 | BP-2023-24-550 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Implementation of RUNIA and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000220/2022-2023 | 98/RD/PHE | 19/01/2023 | 01/01/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 451 | 151.35 | 33.56 | 10
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Runia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012037) | Assistant Engineer - I | Junior Engineer-07 | ORD/000536/2023-2024 | 2530/MLMD | 04/08/2023 | 27/10/2025 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 24.9 | 20.81 | 83.59 | 90
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RUNIA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000467/2023-2024 | 575/RD/PHE | 05/03/2024 | 28/02/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 22.94 | 4.84 | 21.12 | 75
Total | [13 empty] | 642.51 | 177 | 27.55