## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 2199/RD/PHE | 14/12/2022 | 14/12/2022 | Resource Division | 59.08 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Runia PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000448/2024-2025 | 3760/RD/PHED | 18/12/2024 | 01/02/2025 | AJIT PRAMANIK | 74.5 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Runia, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03531/2023-2024 | BP-2023-24-551 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 5.83 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Runia Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03530/2023-2024 | BP-2023-24-550 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Implementation of RUNIA and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000220/2022-2023 | 98/RD/PHE | 19/01/2023 | 01/07/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 451 | 151.35 | 33.56 | 10
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Runia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012037) | Assistant Engineer - I | Junior Engineer-07 | ORD/000536/2023-2024 | 2530/MLMD | 04/08/2023 | 27/10/2025 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 24.9 | 20.81 | 83.59 | 90
7 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RUNIA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000467/2023-2024 | 575/RD/PHE | 05/03/2024 | 28/02/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 22.94 | 4.84 | 21.12 | 75
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12109 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.28 | 5.53 | 100
Total | [13 empty] | 647.5 | 177.28 | 27.38