## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12110 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 2177/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 27.08 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12110 | New | Implementation of BIRGHAI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000225/2022-2023 | 288/RD/PHE | 01/02/2023 | 01/07/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 560.3 | 49.62 | 8.86 | 15
3 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12110 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Birghai Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011862) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000392/2023-2024 | 2400/MLMD | 28/07/2023 | 26/06/2026 | MERCURY ENGINEERING COMPANY. | 26.79 | 0 | 0 | 34
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12110 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BIRGHAI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000466/2023-2024 | 574/RD/PHE | 05/03/2024 | 19/04/2024 | M/S POYEM ENTERPRISE | 22.57 | 0 | 0 | 70
5 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district | SM/12110 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Birghai PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000481/2024-2025 | 14/RD/PHE | 02/01/2025 | 29/09/2025 | DULAL MAJUMDER | 78.38 | 0 | 0 | 0
Total | [13 empty] | 715.13 | 49.62 | 6.94