## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 2198/RD/PHE | 14/12/2022 | 14/12/2022 | Resource Division | 67.14 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of CHADGAON PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001951/2023-2024 | 4003276603 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 3.88 | 3.88 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of CHADGAON PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001950/2023-2024 | 4003276544 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 3.87 | 3.87 | 100 | 100
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Chadgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013024) | Assistant Engineer - I | Junior Engineer-07 | ORD/000187/2023-2024 | 2113/MLMD | 05/07/2023 | 13/12/2025 | DAS CONSTRUCTION | 24.15 | 21.71 | 89.91 | 89
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHADGAON Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000471/2023-2024 | 579/RD/PHE | 05/03/2024 | 19/04/2024 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.57 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | Construction of Culvert with Hume Pipe Across PWD Borrow Pit for making accessible Road at Chandgaon PWSS Head Work Site at Kaliyaganj Block under Raiganj Division, P.H.E. Dte., Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000144/2024-2025 | 3009/RD/PHE | 03/10/2024 | 02/11/2024 | PINTU SWARNAKAR | 2.17 | 2.16 | 99.92 | 100
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | Balance work i.c.w. Construction of boundary wall of Chandgaon piped water supply scheme of Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000402/2025-2026 | 1608/RD/PHE | 17/06/2025 | 15/10/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 3.36 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | Implementation of CHADGAON andit's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000205/2022-2023 | 74/RD/PHE | 16/01/2023 | 09/02/2025 | UJJWAL DAS | 408.1 | 304.43 | 74.6 | 80
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chandgaon PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000423/2024-2025 | 3735/RD/PHE | 18/12/2024 | 02/05/2025 | UJJWAL DAS | 56.93 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12112 | New | Trial Run For Chandgaon PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000674/2024-2025 | 520/RD/PHE | 12/02/2025 | 13/05/2025 | UJJWAL DAS | 0.88 | 0 | 0 | 0
Total | [13 empty] | 593.04 | 336.06 | 56.67