## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 2184/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 30.98 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of LAXMIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000429/2023-2024 | 4003201648 | 29/07/2023 | 27/10/2023 | W.B.S.E.D.C.LTD | 5.21 | 5.21 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of LAXMIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000430/2023-2024 | 4003201640 | 29/07/2023 | 27/10/2023 | W.B.S.E.D.C.LTD | 5.73 | 5.73 | 100 | 100
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Laxmipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013047) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000110/2023-2024 | 1118/MLMD | 23/06/2023 | 12/01/2026 | HANNAN BUILDERS PVT. LTD. | 26.14 | 22.37 | 85.58 | 85
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under LAXMIPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000476/2023-2024 | 584/RD/PHE | 05/03/2024 | 19/04/2024 | M/S P.S. ENTERPRISE | 22.91 | 17.05 | 74.4 | 40
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Implementation of LAXMIPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000250/2022-2023 | 296/RD/PHE | 01/02/2023 | 01/01/2026 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 580.95 | 375.03 | 64.55 | 65
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Uttar Laxmipur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000428/2024-2025 | 3740/RD/PHE | 18/12/2024 | 31/07/2025 | M/S MAA TARA CONSTRUCTION | 35.64 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Balance pipe line for providing functional household tap bconnection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Laxmipur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000473/2024-2025 | 06/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 56.25 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Trial Run For Laxmipur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000679/2024-2025 | 525/RD/PHE | 12/02/2025 | 13/05/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0 | 0
Total | [13 empty] | 764.69 | 425.4 | 55.63