## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 2184/RD/PHE | 12/12/2022 | 12/12/2022 | Resource Division | 30.98 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of LAXMIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000429/2023-2024 | 4003201648 | 29/07/2023 | 27/10/2023 | W.B.S.E.D.C.LTD | 5.21 | 5.21 | 100 | 100
3 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of LAXMIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000430/2023-2024 | 4003201640 | 29/07/2023 | 27/10/2023 | W.B.S.E.D.C.LTD | 5.73 | 5.73 | 100 | 100
4 | UTTAR DINAJPUR | Kaliaganj | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Laxmipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013047) | Assistant Engineer - I | Junior Engineer-04,Junior Engineer-07 | ORD/000110/2023-2024 | 1118/MLMD | 23/06/2023 | 12/05/2026 | HANNAN BUILDERS PVT. LTD. | 26.14 | 22.37 | 85.58 | 85
5 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under LAXMIPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000476/2023-2024 | 584/RD/PHE | 05/03/2024 | 19/04/2024 | M/S P.S. ENTERPRISE | 22.91 | 17.05 | 74.4 | 40
6 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Implementation of LAXMIPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000250/2022-2023 | 296/RD/PHE | 01/02/2023 | 01/01/2026 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 580.95 | 375.03 | 64.55 | 65
7 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Uttar Laxmipur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000428/2024-2025 | 3740/RD/PHE | 18/12/2024 | 31/07/2025 | M/S MAA TARA CONSTRUCTION | 35.64 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Balance pipe line for providing functional household tap bconnection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Laxmipur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000473/2024-2025 | 06/RD/PHE | 02/01/2025 | 16/02/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 56.25 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Trial Run For Laxmipur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000679/2024-2025 | 525/RD/PHE | 12/02/2025 | 13/05/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 11/04/2024 | HORIZEN | 5 | 0.19 | 3.77 | 100
11 | UTTAR DINAJPUR | Kaliaganj | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district | SM/12115 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
Total | [13 empty] | 774.68 | 425.58 | 54.94