## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. | SM/12393 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 2171/RD/PHE | 09/12/2022 | 09/12/2022 | Resource Division | 34.71 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. | SM/12393 | Augmentation | Augmentation of DHARAMPUR Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at Goalpukhur-I & II Block of Uttar Dinajpur District under Raiganj Division, PHE Dte.. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000216/2022-2023 | 114/RD/PHE | 20/01/2023 | 01/04/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 388.45 | 159.81 | 41.14 | 74
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. | SM/12393 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components, making compound lighting arrangement and grid connected ground mounted solar PV system with net metering at T/W no. I of Augmentation of Dharampur (Zone-I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/013310) | Assistant Engineer - I | Junior Engineer-02 | ORD/000163/2023-2024 | 2088/MLMD | 04/07/2023 | 29/12/2028 | DILIP MAHATO. | 21.41 | 0 | 0 | 45
4 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. | SM/12393 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Dharampur Water Supply Scheme, (Zone- I) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/002488/2023-2024 | 809/MLMD | 15/02/2024 | 01/08/2025 | MAA BHABOTARINE ENTERPRISE | 10.76 | 4.99 | 46.34 | 89
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. | SM/12393 | Augmentation | Additional Pipe Line and other ancillary works to provide FHTC at DHARAMPUR ZONE-I PWSS in connection with augmentation of Dharampur PWSS at Goalpokher-I Block under Islampur Sub-Division, P.H.E. Dte. under Raiganj Division ,PHED, Uttar Dinajpur. | Assistant Engineer ISD |  | ORD/000131/2024-2025 | 3022/RD/PHE | 03/10/2024 | 17/11/2024 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 33.34 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. | SM/12393 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. | SM/12393 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dharampur Zone-I Water Supply Scheme (Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000340/2025-2026 | 2489/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0 | 0
Total | [13 empty] | 524.41 | 164.8 | 31.43