## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | SM/12394 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 2172/RD/PHE | 09/12/2022 | 09/12/2022 | Resource Division | 40.38 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | SM/12394 | Augmentation | Augmentation of DHARAMPUR Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000215/2022-2023 | 125/RD/PHE | 20/01/2023 | 01/04/2025 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 363.42 | 155.55 | 42.8 | 60
3 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | SM/12394 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components, making compound lighting arrangement and grid connected ground mounted solar PV system with net metering at T/W no. I of Augmentation of Dharampur (Zone-II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013311) | Assistant Engineer - I | Junior Engineer-02 | ORD/000164/2023-2024 | 2089/MLMD | 04/07/2023 | 29/12/2028 | DILIP MAHATO. | 21.42 | 9.64 | 45.04 | 45
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | SM/12394 | Augmentation | Laying & Distribution pipeline at Dharampur Zone-II in connection with Augmentation of DHARAMPUR Zone-II at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.( Laying Distribution pipe line.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000427/2023-2024 | 3342/RD/PHE | 06/12/2023 | 20/01/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 71.53 | 68.71 | 96.06 | 60
5 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | SM/12394 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Dharampur Water Supply Scheme, (Zone- II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013311) | Assistant Engineer - I | Junior Engineer-02 | ORD/000193/2023-2024 | 2092/MLMD | 04/07/2023 | 02/10/2023 | S.P. ENTERPRISE (SILIGURI) | 10.66 | 10.61 | 99.51 | 99
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | SM/12394 | Augmentation | Construction of Approach Road in connection with Augmentation of Dharampur Zone-II PWSS at Goalpokhur-I Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000340/2024-2025 | 3296/RD/PHE | 20/11/2024 | 05/12/2024 | KULICK ENTERPRISE | 3.77 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | SM/12394 | Augmentation | Inter-connecting various CIDF Pipe & with main delivery line and other ancillary works for Dharampur Zone- II Piped Water Supply Scheme (Augmentation Dharampur Zone-II)under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD |  | ORD/000132/2024-2025 | 3023/RD/PHE | 03/10/2024 | 23/10/2024 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 8.8 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. | SM/12394 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dharampur Zone-II Water Supply Scheme(Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000342/2025-2026 | 2490/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0 | 0
Total | [13 empty] | 550.9 | 244.52 | 44.39