## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Chopra | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme | SM/12396 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1036/RD/PHE | 04/04/2023 | 04/04/2023 | Resource Division | 25.91 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Chopra | Malda Mechanical | BARA DOPAHARU Piped Water Supply Scheme | SM/12396 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bara Dopaharu Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014803) | Assistant Engineer - I | Junior Engineer-02 | ORD/000454/2023-2024 | 2478/MLMD | 04/08/2023 | 11/02/2026 | ANIMA ENTERPRISE | 28.34 | 21.02 | 74.16 | 74
3 | UTTAR DINAJPUR | Chopra | Malda Mechanical | BARA DOPAHARU Piped Water Supply Scheme | SM/12396 | New | Quotation for new service connection at BARA DOPAHARU PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12396) |  |  | BILL/01086/2024-2025 | BP-2024-25-307 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 18.64 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Chopra | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme | SM/12396 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 7213.93 | 110.72 | 1.53 | 30
5 | UTTAR DINAJPUR | Chopra | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme | SM/12396 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bara Dopaharu Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000310/2025-2026 | 1978/RD/PHE | 03/07/2025 | 30/12/2025 | MONDAL PRECISION PRIVATE LIMITED | 18.74 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Chopra | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme | SM/12396 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at BARA DOPAHARU PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000385/2025-2026 | 2097/RD/PHE | 15/07/2025 | 11/01/2026 | M/S SACHIN KUMAR | 43.32 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Chopra | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme | SM/12396 | New | Providing FHTC in connection with Bara Dopaharu Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000389/2025-2026 | 2174/RD/PHE | 25/07/2025 | 23/10/2025 | M/S SHIB ENTERPRISE | 5.4 | 0 | 0 | 0
Total | [13 empty] | 7354.29 | 131.74 | 1.79