## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Barbila Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014694) | Assistant Engineer - I | Junior Engineer-02 | ORD/000448/2023-2024 | 2474/MLMD | 04/08/2023 | 27/05/2026 | DILIP MAHATO. | 26.3 | 13.25 | 50.39 | 72
2 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 11/08/2026 | ROY ENGINEERS. (PATNA) | 6530.5 | 73.35 | 1.12 | 38
3 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1119/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 27.72 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 | New | Quotation for new service connection at BARBILA PH-I (Goalpokher ccc) in the district of Uttar Dinajpur. |  |  | BILL/03734/2023-2024 | BP-2023-24-694 | 15/03/2024 | 15/03/2024 | W.B.S.E.D.C.LTD | 6.4 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 | New | Quotation for new service connection at BARBILA PH-II (Goalpokher ccc) in the district of Uttar Dinajpur. |  |  | BILL/03733/2023-2024 | BP-2023-24-693 | 15/03/2024 | 15/03/2024 | W.B.S.E.D.C.LTD | 19.74 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 | New | Construction of concrete pathway with land development at Head Work Site Pump House & 2nd TW Site Pump House for BARABILLA Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000018/2025-2026 | 1202/RD/PHE | 25/04/2025 | 09/06/2025 | GULJAN BEGAM | 9.98 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. | SM/12443 | New | Providing FHTC in connection with Barobilla Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000024/2025-2026 | 1179/RD/PHE | 23/04/2025 | 08/05/2025 | HAQUE CONSTRUCTION | 6.94 | 0 | 0 | 0
Total | [13 empty] | 6632.37 | 86.6 | 1.31