## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Islampur | Malda Mechanical | BANIKANER ALISA RAHATPUR PWSS | SM/12522 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of BANIKANER ALISA RAHATPUR , Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000655/2023-2024 | 4003194822 | 18/07/2023 | 16/10/2023 | W.B.S.E.D.C.LTD | 7.99 | 7.99 | 100 | 100
2 | UTTAR DINAJPUR | Islampur | Malda Mechanical | BANIKANER ALISA RAHATPUR PWSS | SM/12522 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of BANIKANER ALISA RAHATPUR,Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000650/2023-2024 | 4003199237 | 25/07/2023 | 23/10/2023 | W.B.S.E.D.C.LTD | 10.46 | 10.46 | 100 | 100
3 | UTTAR DINAJPUR | Islampur | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS | SM/12522 | New | Material Requisition To Resource Division |  |  | RTOR000121/2022-2023 | 616/RD/PHE | 28/02/2023 | 28/02/2023 | Resource Division | 25.55 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Islampur | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS | SM/12522 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BANIKANER ALISA PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD |  | ORD/000486/2023-2024 | 597/RD/PHE | 05/03/2024 | 19/04/2024 | K.G.N BUILDERS | 22.57 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Islampur | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS | SM/12522 | New | Implementation of BANIKANER ALISA RAHATPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000302/2022-2023 | 551/RD/PHE | 23/02/2023 | 01/04/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 232.41 | 79.78 | 34.33 | 80
6 | UTTAR DINAJPUR | Islampur | Malda Mechanical | BANIKANER ALISA RAHATPUR PWSS | SM/12522 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Banikaner Alisa Rahatpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014361) | Assistant Engineer - I | Junior Engineer-02 | ORD/000456/2023-2024 | 2479/MLMD | 04/08/2023 | 27/01/2026 | M/S TRILOCHAN CONSTRUCTION CO. | 25.38 | 18.14 | 71.47 | 78
7 | UTTAR DINAJPUR | Islampur | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS | SM/12522 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Banikaner Alisa Rahatpur PWSS at Islampur Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000167/2024-2025 | 2895/RD/PHE | 25/09/2024 | 15/10/2024 | SHANKAR SAHA | 4.31 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Islampur | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS | SM/12522 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BENIKANER ALIAS RAHATPUR PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000371/2024-2025 | 3490/RD/PHE | 02/12/2024 | 01/01/2025 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 14.85 | 0 | 0 | 0
Total | [13 empty] | 343.52 | 116.38 | 33.88