## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARA SINGHANATH Piped Water Supply Scheme | SM/12529 | New | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1120/RD/PHE | 24/04/2023 | 24/04/2023 | Resource Division | 37.22 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | BARA SINGHANATH Piped Water Supply Scheme | SM/12529 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of BARA SINGHANATH, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02493/2023-2024 | BP-2023-24-429 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 5.7 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | BARA SINGHANATH Piped Water Supply Scheme | SM/12529 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of BARA SINGHANATH, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02494/2023-2024 | BP-2023-24-430 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 3.96 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARA SINGHANATH Piped Water Supply Scheme | SM/12529 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at BARA SINGHNATH PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000267/2025-2026 | 2086/RD/PHE | 14/07/2025 | 10/01/2026 | ROY ENGINEERS. (PATNA) | 45.73 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Goalpokhar-I | Malda Mechanical | BARA SINGHANATH Piped Water Supply Scheme | SM/12529 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Barasinghanath Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014476) | Assistant Engineer - I | Junior Engineer-02 | ORD/000438/2023-2024 | 2473/MLMD | 04/08/2023 | 29/09/2025 | DILIP MAHATO. | 27.32 | 0 | 0 | 84
6 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARA SINGHANATH Piped Water Supply Scheme | SM/12529 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 16 nos. Piped water supply Schemes within GOALPOKHAR-I Dev. Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2023-2024 | 2568/RD/PHE | 01/09/2023 | 14/11/2025 | ROY ENGINEERS. (PATNA) | 6530.5 | 333.58 | 5.11 | 38
7 | UTTAR DINAJPUR | Goalpokhar-I | Raiganj Division | BARA SINGHANATH Piped Water Supply Scheme | SM/12529 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bara Singhanath Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000314/2025-2026 | 1984/RD/PHE | 04/07/2025 | 31/12/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0 | 0
Total | [13 empty] | 6681.36 | 333.58 | 4.99