## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12638 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 2392/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.57 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12638 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Biprit Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015258) | Assistant Engineer - I | Junior Engineer-02 | ORD/000436/2023-2024 | 2472/MLMD | 04/08/2023 | 27/05/2026 | M/S SABANA CONSTRUCTION | 10.8 | 9.09 | 84.17 | 84
3 | UTTAR DINAJPUR |  | Raiganj Division | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12638 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Biprit Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000149/2022-2023 | 1927/RD/PHE | 28/10/2022 | 12/12/2022 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 33.13 | 0 | 0 | 60
Total | [13 empty] | 46.51 | 9.09 | 19.55