## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12641 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Baruna PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001949/2023-2024 | 4003276648 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 3.92 | 3.92 | 100 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12641 | Augmentation | Source(Rig Bored Tube-Well) Augmentation of Baruna Piped Water Supply Scheme of Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000120/2022-2023 | 1907/RD/PHE | 28/10/2022 | 12/12/2022 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 25.99 | 16.02 | 61.65 | 65
3 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12641 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 21/RD/PHE | 03/01/2024 | 03/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12641 | Augmentation | Additional Quotation charge at TW No- III of Baruna, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03723/2023-2024 | BP-2023-24-704 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 1.41 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12641 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Baruna Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015272) | Assistant Engineer - I | Junior Engineer-07 | ORD/000414/2023-2024 | 2467/MLMD | 04/08/2023 | 19/03/2025 | JOY ENTERPRISE. | 10.54 | 2.42 | 22.99 | 100
Total | [13 empty] | 43.28 | 22.36 | 51.67