## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12642 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Gutin Piped Water Supply Scheme of Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000138/2022-2023 | 1916/RD/PHE | 28/10/2022 | 27/03/2025 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 39.77 | 16.49 | 41.48 | 75
2 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12642 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Gutin PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001953/2023-2024 | 4003279197 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 3.62 | 3.62 | 100 | 100
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12642 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Gutin Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/000321/2024-2025 | 2948/MLMD | 11/09/2024 | 01/03/2025 | SUDIP DEY | 10.46 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12642 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 15/RD/PHE | 03/01/2024 | 03/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
Total | [13 empty] | 55.27 | 20.11 | 36.39