## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12643 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Chhotaparua Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000136/2022-2023 | 1914/RD/PHE | 28/10/2022 | 07/12/2023 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 30.69 | 0 | 0 | 50
2 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12643 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 18/RD/PHE | 03/01/2024 | 03/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12643 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Chhotaparua , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02469/2023-2024 | BP-2023-24-398 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 8.35 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12643 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Chhotaparua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015259) | Assistant Engineer - I | Junior Engineer-07 | ORD/000768/2023-2024 | 2484/MLMD | 04/08/2023 | 19/02/2025 | SUBRATA KUMAR DAS. | 11.37 | 0 | 0 | 100
Total | [13 empty] | 51.83 | 0 | 0