## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Malda Mechanical | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12644 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Sitgram,PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001963/2023-2024 | 4003270394 | 06/12/2023 | 05/03/2024 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12644 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Sitgram Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000141/2022-2023 | 1919/RD/PHE | 28/10/2022 | 12/12/2022 | BHOLA PAUL | 31.5 | 0 | 0 | 30
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12644 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Sitgram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015290) | Assistant Engineer - I | Junior Engineer-07 | ORD/000694/2023-2024 | 2769/MLMD | 14/08/2023 | 10/02/2024 | J.S. ERECTORS. | 10.51 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12644 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 20/RD/PHE | 03/01/2024 | 03/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12644 | Augmentation | Ancillary work I.C.W. retrofitting of Sitgram PWSS, Raiganj Block in connection with Augmentation of Sitgram PWSS under Raiganj Division, PHE Dte. Uttar Dinajpur | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000054/2025-2026 | 1544/RD/PHE | 11/06/2025 | 11/07/2025 | M/S. BANGARAJ | 2.03 | 0 | 0 | 0
Total | [13 empty] | 49.71 | 0 | 0