## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12647 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Ghirnigaon Khas Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000147/2022-2023 | 1925/RD/PHE | 28/10/2022 | 12/12/2022 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 33.2 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12647 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Ghirnigaonkhas Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015286) | Assistant Engineer - I | Junior Engineer-02 | ORD/000356/2023-2024 | 2367/MLMD | 28/07/2023 | 26/06/2026 | SOVON KUMAR DAS. | 10.57 | 9.18 | 86.85 | 87
3 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12647 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 2398/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.48 | 0 | 0 | 0
Total | [13 empty] | 46.25 | 9.18 | 19.85