## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12648 | Augmentation | Source(Rig Bored Tube-Well) Augmentation of Bhagabati Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000126/2022-2023 | 1910/RD | 28/10/2022 | 12/12/2022 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 32.3 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12648 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 2401/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.48 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12648 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Bhagabati Water Supply Scheme in the District of Uttar DInajpur under Malda Mechanical Division, PHE Dte. (TSM/015035) | Assistant Engineer - I | Junior Engineer-02 | ORD/001803/2023-2024 | 3690/MLMD | 29/11/2023 | 29/11/2025 | SUBRATA KUMAR DAS. | 10.57 | 9.18 | 86.85 | 87
4 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12648 | Augmentation | Quotation for new service connection at Source Aug of BHAGABATI PH-III (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00022/2024-2025 | BP-2024-25-57 | 09/04/2024 | 09/04/2024 | W.B.S.E.D.C.LTD | 5.58 | 0 | 0 | 0
Total | [13 empty] | 50.93 | 9.18 | 18.03