## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12649 | Augmentation | Source(Rig Bored Tube-Well) Augmentation of Dakshin Kundal Pukur Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000125/2022-2023 | 1909/RD/PHE | 28/10/2022 | 12/12/2022 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 32.3 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12649 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 2396/RD/PHE | 17/08/2023 | 17/08/2023 | Resource Division | 2.48 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12649 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Dakshin Kundalpukur Water Supply Scheme in the District of Uttar DInajpur under Malda Mechanical Division, PHE Dte. (TSM/002870) | Assistant Engineer - I | Junior Engineer-02 | ORD/000606/2023-2024 | 2651/MLMD | 10/08/2023 | 26/06/2026 | PABITRA MANDAL | 10.54 | 0 | 0 | 86
Total | [13 empty] | 45.32 | 0 | 0