## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12651 | Augmentation | Source(Rig Bored Tube-Well) Augmentation of Kotar Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000124/2022-2023 | 1908/RD/PHE | 28/10/2022 | 06/03/2024 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 32.51 | 18.64 | 57.34 | 30
2 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12651 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Kotar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015244) | Assistant Engineer - I | Junior Engineer-02 | ORD/000358/2023-2024 | 2369/MLMD | 28/07/2023 | 18/11/2024 | SUBRATA KUMAR DAS. | 10.55 | 10.53 | 99.84 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12651 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 11/RD/PHE | 03/01/2024 | 03/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | SM/12651 | Augmentation | Quotation for new service connection at Source Augmentation of KOTAR PH-III (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12651) |  |  | BILL/01056/2024-2025 | BP-2024-25-240 | 29/05/2024 | 29/05/2024 | W.B.S.E.D.C.LTD | 4.39 | 0 | 0 | 0
Total | [13 empty] | 48.87 | 29.17 | 59.69